## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Collect ANPR & ATCC dataset from Kaggle; validate images & videos | MUST HAVE | Kaggle Account | Gangavaram Mounika | Completed
S1 | S1 | US-002 | Perform initial preprocessing: resizing, denoising, normalization | MUST HAVE | OpenCV | Gangavaram Mounika | Completed
S1 | S1 | US-003 | Conduct EDA on traffic patterns, number plate structure, vehicle classes | SHOULD HAVE | Python Libraries | Gangavaram Mounika | Completed
S1 | S1 | US-004 | Set up YOLO + OCR environment; verify GPU compatibility | MUST HAVE | CUDA / Kaggle GPU | Gangavaram Mounika | Completed
S2 | S2 | US-001 | Outlier removal & scaling for numeric features used in analytics pipelines | MUST HAVE | — | Gangavaram Mounika | Completed
S2 | S2 | US-002 | Data encoding and plate-level metadata preparation (categorical handling) | MUST HAVE | — | Gangavaram Mounika | Completed
S2 | S2 | US-003 | Train detection & classification models (YOLO for plates/vehicles) and evaluate | MUST HAVE | YOLOv8 | Gangavaram Mounika | Completed
S2 | S2 | US-004 | Identify best-performing model(s) using evaluation metrics (mAP, F1) | MUST HAVE | Scikit-Learn | Gangavaram Mounika | Completed
S2 | S2 | US-005 | Hyperparameter tuning and retraining on best model | MUST HAVE | — | Gangavaram Mounika | Completed
S2 | S2 | US-006 | Prepare finalized ANPR model artifacts for integration/deployment | MUST HAVE | — | Gangavaram Mounika | Completed
S3 | S3 | US-001 | Create prototype Streamlit webpage to display detections, plates, counts | MUST HAVE | Streamlit | Gangavaram Mounika | Completed
S3 | S3 | US-002 | Develop interface for Streamlit or hosting | MUST HAVE | Flask, PythonAnywhere | Gangavaram Mounika | Completed
S3 | S3 | US-003 | Integrate OCR output into UI (show recognized plate text with confidence) | MUST HAVE | OCR Library | Gangavaram Mounika | Completed
S3 | S3 | US-004 | Implement logging: timestamped plate records, vehicle class, location ID | SHOULD HAVE | DB / CSV | Gangavaram Mounika | Completed
S4 | S4 | US-001 | Develop conversational/alert feature (optional) or integrate basic alerts | MUST HAVE | GrogAI/Streamlit | Gangavaram Mounika | Completed
S4 | S4 | US-002 | Integrate ANPR & ATCC modules into single Streamlit app and test end-to-end | COULD HAVE | Streamlit | Gangavaram Mounika | Completed
S4 | S4 | US-003 | Final integration, performance tuning, and inference-time optimizations | MUST HAVE | — | Gangavaram Mounika | Completed
S4 | S4 | US-004 | Prepare final documentation, demo script, and project PPT for submission by Dec 8 | MUST HAVE | Docs, PPT | Gangavaram Mounika | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 50 | 9 | 12 | 14 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TASK-001 | Setup project structure & GitHub repo | 2025-11-08 | 2025-11-08 | - | Setup | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Install YOLO, Streamlit, OCR dependencies | 2025-11-08 | 2025-11-09 | - | Environment Setup | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-003 | Upload ATCC dataset to Drive | 2025-11-09 | 2025-11-10 | - | Data Gathering | Completed | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-004 | Upload ANPR dataset to Drive | 2025-11-10 | 2025-11-11 | - | Data Gathering | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-005 | Perform EDA on ANPR & ATCC datasets | 2025-11-11 | 2025-11-14 | - | Data Analysis | Completed | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-004 | TASK-006 | Extract frames from ATCC videos | 2025-11-15 | 2024-11-16 | - | Data Processing | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-007 | Train ATCC YOLO model (Colab) | 2025-11-16 | 2024-11-18 | - | Model Training | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-008 | Train ANPR YOLO model | 2025-11-18 | 2024-11-20 | - | Model Training | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-009 | Test OCR results with EasyOCR | 2025-11-20 | 2024-11-21 | - | OCR Testing | Completed | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TASK-010 | Export YOLO results to CSV | 2025-11-21 | 2024-11-21 | - | Data Export | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-007 | TASK-011 | Build Streamlit ATCC UI | 2025-11-22 | 2024-11-24 | - | Frontend | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TASK-012 | Build Streamlit ANPR UI | 2024-11-24 | 2024-11-26 | - | Frontend | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TASK-013 | Integrate YOLO with Streamlit front-end | 2024-11-26 | 2024-11-27 | - | Integration | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TASK-014 | Add bar, pie, line & scatter charts | 2024-11-27 | 2024-11-28 | - | Visualization | Completed | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TASK-015 | Setup SQLite DB for storage | 2024-11-28 | 2024-11-28 | - | Database | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-010 | TASK-016 | Final UI polishing for ATCC & ANPR | 2024-11-29 | 2024-12-01 | - | UI/UX | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TASK-017 | Full system end-to-end testing | 2024-12-01 | 2024-12-04 | - | Testing | Completed | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | TASK-018 | Fix bugs & improve performance | 2024-12-04 | 2024-12-06 | - | Debugging | Completed | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | TASK-019 | Deploy final system in VS Code | 2024-12-06 | 2024-12-07 | - | Deployment | Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | TASK-020 | Documentation + Final Demo | 2024-12-07 | 2024-12-08 | - | Documentation | Completed | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | Lack of clarity in overall ANPR + ATCC project roadmap | Conducted detailed discussion with mentor for roadmap clarification
S1 | Day 5 | Confusion in dataset structure and requirements | Mentor provided dataset explanation and sample processing steps
S1 | Day 7 | Errors while installing YOLO and EasyOCR in Colab | Mentor shared correct installation commands and troubleshooting steps
S2 | Day 12 | Difficulty understanding Colab training pipeline for YOLO | A detailed explanation was given by mentor with examples
S2 | Day 14 | Slow GPU processing for ATCC videos | Optimized video frame extraction as per mentor guidelines
S2 | Day 15 | Model output not saving correctly to Drive | Mentor helped restructure Drive folder permissions
S3 | Day 20 | Difficulty implementing virtual environment in VS Code | Explained by mentor through live screen sharing
S3 | Day 23 | Streamlit not detecting installed packages | Mentor guided to reinstall dependencies in the venv
S3 | Day 25 | Difficulty filling Agile documentation | A dedicated session was held to explain Agile documentation format
S4 | Day 35 | Errors while integrating ANPR OCR with Streamlit | Mentor resolved via code review and correction
S4 | Day 45 | Logical error in vehicle counting output | Discussed in meeting and resolved by modifying count loop
S4 | Day 55 | UI alignment and dashboard layout issues | Solved after guidance on Streamlit layout design
S4 | Day 57 | Difficulty preparing PowerPoint and project summary | Resolved via meeting and mentor-provided structure

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-11-04 | 2025-11-17 | Gangavaram Mounika | Exploring Drive links for self study | Time waste in documentation | Regular coding | Focused on Organization
2 | S2 | 2025-11-18 | 2025-11-25 | Gangavaram Mounika | Implementing advanced preprocessing | Skipping daily coding task | Experimenting | Enhanced preprocessing techniques
3 | S3 | 2025-11-25 | 2025-12-13 | Gangavaram Mounika | Regularly commit git Changes | Procastinating | Maintaining Workflow | Improved version control
4 | S4 | 2025-12-05 | 2025-12-27 | Gangavaram Mounika | Learning Groq Ai | Watching Tutorials | Reading Documentaion | Gained familiarity